## Feuil1
ADMT13 Action List Updated on the 12th August 2013
| Action | Target Date | Responsibility | Priority | Status | DONE
Real Time Data Stream
1 | Run the check every Quarter and sent report to DACs . AIC should be involved in the feedback and monitoring of correction as for Altimetry check | AST14 | Anh and Mathieu | H | Done in August 2013 | x
2 | Study the timeliness of BUFR for all DACs that are much below the 90% target | ADMT14 | All DACs | R | first result in August report to be checked by DACS | x
3 | Each DAC to check header they are sending to GTS (both TESAC and BUFR)– should be on Anh's list. | December 2012 | All DACs | H | csiro - Done ; kordi GTS data handled by CLS so no action necessary by them; jma done; incois has issues with tesacs not being seen by meteo france though japan and others are seeing the data. They are coding bufr but not sending it out until the tesac problem is solved. I asked them to send a bufr sample to Anh and perhaps consider sending the bufr onto the gts because they might get through even if tesacs are disappearing - by end of month. ok for the other DACs Nothing received from KMA - no bufr yet - tested. sent test files to check Anh said can't read the file. jamstec says is OK. so send to GTS and send header to Anh. nmdis handled by cls
4 | Anh to coordinate with Mathieu to separate floats by telecommunications methods – Argos vs Iridium to see if the delays are correlated with communications system | AST14 | Anh and Mathieu | R | done | x
5 | CSIO don’t have any adjusted fields at GDAC. They should have some if they were applying the Surface pressure correction for APEX. To be investigated. | AST14 | CSIO | H | have been informed - no information received.
6 | The list of the anomalies detected for Adjusted parameters will be included in next anomaly report done By Coriolis | January 2013 | Christine | R | done in March report but not in the following ( To be checked by Christine) | x
7 | AOML has anomaly on mixed DM and RT float that seems to be due to DM resubmission | AST14 | Claudia & Elizabeth | H | Done | x
8 | all DACS to run the new density test on the reference profile that Thierry put on the argodatamgt web site to test there density test . | AST14 | All DACs | R | CSIRO done; JMA has issue with file formats so cannot do this yet; kordi and incois outcome will be same as for csiro once done Done for Meds started AOML Coriolis done kma unknown - will check (probably not) to be done at BODC nmdis done
9 | Document the Near Surface Temperature procedure in RTQC manual | AST14 | Justin/Clare/Annie | R | done The manual has been provided by Justin | x
10 | All DACs to provide feedback on Near Surface T surface procedure | ADMT14 | All DACs | R | There is now a document on real-time qc for near surface data.This document consists of feedbacks from BODC, Coriolis, MEDS, AOML. Annie plans to include this in the next version of the qc manual after ADMT in october | x
11 | Look at AIC report and solve the issue about coherency between AIC/ GTS /GDAC | AST14 | DACs | H | For German Floats the reason is that they were too late for delivery on GTS and therefore only present at GDAC To be done for French floats Done regulary by AOML, BODC to be checked by MEDS
12 | DACs have to look at their process to check unnecessary delays and chaining processing as much as possible. | ADMT14 | DACs | R | delays have improved markedly but room for more work | x
13 | DACs to implement the 2047db anomaly detection described by Cecile. Document in cookbook and RTQC manual | ASAP | Coriolis, INCOIS , CSIO, JMA | R | JMA is still working towards this - it's complicated; incois has only one profile from one (dead) float and will fix this by hand. Done at Coriolis
14 | Continue to progress on DOI issue | ADMT14 | Justin and Thierry | R | Feedback will be provided at ADMT14 | x
15 | Document RTQC procedure for Oxygen | AST14 | Virginie and Thierry | R | The RTQC manual has been updated and validated | x
Pressure Correction
16 | Generate adjusted fields for APEX when SP=0 | AST14 | AOML, CSIO, KMA, Coriolis | H | Done for German floats kma working on it. Done for Coriolis started at AOML CSIO - progress unknown
17 | DMQC rt files with all bad data so they don’t contaminate the data set | ADMT14 | DAC mentioned in CSIRO audit | R | Done for German floats To be done at AOML Pb that its mainly Argo equiv started BODC started at MEDS
18 | Correct pressure for floats that don't auto-correct for surface pressure offset | AST14 | AOML,BODC,CORIOLIS,MEDS, CSIO,KMA, KORDI | H | Done for German floats kma - working on this kordi done started BODC done at AOML ( except SP=0 see action 16)
19 | Correct TNPD profiles that haven’t been correctly treated – simply add required comment and fields and QC values and errors | AST14 | AOML,BODC,CORIOLIS,JMA,MEDS, KMA, INCOIS | H | Done for German floats and French floats kma - working on this Bodc Done started at Meds Claudia to check with US DM Operators jma is contacting jamstec - they're working towards this; this appears to be a problem for Jeff, not Incois - they are working towards getting it sorted out. JAMSTEC used SPO from the next profile to correct so is a timing mismatch between Jeff and them. I've explained it to him and we'll see if he can take this into account.
Reference Database
20 | A specific comparison between ICES and US-NODC to better assess the quality; including looking at slices on the deep ocean to identify potentially offset cruises and remove them. | ADMT14 | Christine | R | Started
21 | Inventory of cruises in Ref DB ( basic ASCII file) | AST14 | Christine and Steve | R | First list was initated and still work to be done together
Delayed Mode processing
22 | The list of orphan floats is in Mathieu report . DM-OPERATORS to be assigned for the remaining US equivalent floats | ASAP | Steve to coordinate | R
23 | DM-Operators to correct the D-files where anomalies we listed by John | AST14 | All DM Operators | H | almost done for BSH for Coriolis Done BODC To be checked by Meds and AOML
24 | Plan for DM workshop in 2013 | 2012-12-01 | Justin and Brian | R | Planned before ADMT ( 14th -15th October 2013 ) | x
GDAC
25 | KORDI and NMDIS don’t have a gray list and probably need update. | AST14 | KORDI, NMDIS | R | kordi grey list delivered in December Will be done for NMDIS
26 | DACS , together with the DM-Operator, should update their gray list to remove the dead floats that have been processed in delayed mode | AST14 | All DACs | H | CSIRO done, kordi done, jma now done; incois done. Coriolis done , BODC done , Meds done, To be checked for AOML, kma checking this, nmdis has only one grey listed float and will put it on a list and submit.
27 | Contingency Plan DACs to stop delivery to US GDAC Notice to be sent to users on US GDAC temporary outage US GDAC either to turn off presence and put a Warning message or move to a mirror of Coriolis GDAC | Dec 2012 |  | H | csiro done, kordi done, kma done, jma done, incois done - Closed on 23rd May as USGDAC back online
28 | Action to AST and FNMOC to validate the change of mission of the US GDAC until it's back working properly and the way to warn the users | Dec 2012 | Susan and Steve | H | done | x
29 | USGDAC to repair the operational operations Update gray list File Removal operation Detailed index-File provision Accept multi-axis format Accept compressed files (.tar.gz) Provide authorization for the DACs that change their server IP address Resynchronize with Coriolis GDAC | AST14 | Mark | H | - Update Greylist: Completed (In discussions with Thierry this week, there will be slight enhancements to this process at both GDACs) - File removal operation: Completed (In discussions with Thierry this week, there will be slight enhancements to this process at both GDACs) - Accept multi-axis format: Completed - Provide authorization for the DACs that change their IP address: Completed - Resynchronize with the French GDAC: Completed - Detailed index-file provision: cone early July - Accept compressed files (.tar.gz): done mid July | x
30 | GDAC to update multi-cycle processing to take into account multi-sensor/multi-axes format | January 2013 | Thierry and Mark | H | Filechecker accept the MultiProfile cycle files . Started but not completed. both GDAC manage multi-profile files for new deliveries. The reprocessing of all of the merged files is scheduled for end May | x
31 | Study if possible to populate automatically from profile file ACDD attributes | January 2013 | Thierry | R | If done it will be done by GDAC while generating the multi-cycle file . So no impact on DACs
32 | GDAC to study how to patch floats that only have one Cycle/Parking_Depth (add CF and extra dimension, Sampling-Schema, Mission_Number=1) as well as patch new profiles until DACs switch to V3.0 format | AST14 | Thierry | R | Started Specification document under preparation
Format
33 | Ann to sent the anomalies of the TECH FILE Audit to DACs and DACs to correct | Dec 2012 | Ann and all DACs | H | tech file audits sent out in Jan 2013, jma corrected, csiro corrected, kordi corrected, incois corrected except for one file that died on deployment - tech file will be removed. Started for Coriolis but still some tech info that should be in Trj file BODC is working on it Done for MEDS Started at AOML no feedback yet from CSIO NMDIS checking
34 | One contact for meta-data from each DAC to send to Esmee | Dec 2012 | All DACs | R | csiro done (Esmee), kordi done (Moon-Sik), jma done (Mizuho), incois done (Uday) MEDS (Anh) AOML (Argo operation adress) Coriolis (Vincent) BODC( argo operation email) , kma - Dr. P-H Chang - see mailing list. | x
35 | Update the meta-data format according to meeting recommendations | Dec 2012 | Esmee and Mathieu | R | Done on format but not on reference tables. Missing input from ADMT. Mathieu to remind people that should contribute
36 | Each DAC to provide with a web page with manual online and link to their decoder | ADMT14 | All DACs | R | Started for UCSD Done at INCOIS, Coriolis,CSIRO other dacs have been reminded
37 | Bio Argo and NST communities to check meta-data section of the manual and the configuration table and decide and advise which variables are required their floats |  | Catherine and Clare | R
38 | Provide to AST for validation the Argo-Group definition | AST14 | Esmee & Mathieu to AST | R | discussed at AST | x
39 | Modify file checker to allow that no ADJUSTED parameter is possible for the PARAM that handle the raw measurement transmitted by a float | AST14 | Thierry and Mark | H | to be done
40 | audit on the parameter that occurs and parameter that are declared in meta-data and profile, trajectory | ADMT14 | Brian, Thierry, Megan, Esmee | R
41 | Update User Manual V3.0 | Dec 2012 | Thierry | H | Exist for Profile and Tech file is fine. Need to add the new Traj3 from Megan and reference table from Mathieu to be cheched
GADR
42 | GADR to switch to CORIOLIS GDAC to perform the monthly archive until USGDAC is back on line | Dec 2012 | Charles SUN | H | done in Dec 2012 | x
43 | Check with US-NODC that the multi--profile files they distribute contain the adjusted variables when present | AST14 | Charles SUN | H | done in May 2013 | x
Trajectory
44 | Modify TrajV3.0 description and cookbook to take into account feedback from meeting | January 2012 | John | R | done | x
45 | Coriolis and Scripps to transform ANDRO data to Traj3.0 until 2009 | June 2013 | Thierry and Megan | R
46 | Elaborate a proposal from CLS and Ifremer to process backlog ( 2009 and onwards) in TrajV3.0 for Kalman filter an processing | AST14 | Yann & Virginie | R | will be presented at Ast14 | x
47 | DAC to process active floats TrajV3.0 | June-ADMT14 | All DACs | R
Recommendations to AST
48 | To AST: how to document the different issues that happened to the Argo data into a document for user information, e.g., pressure correction, micro-leak… | AST13 | AST Chairs | R